## Project Summary
ICCPP Email Intelligence System
Internal email campaign platform — work completed in this project
OVERVIEW
Item | Detail
Project name | ICCPP Email Intelligence System (repo folder: ENG Email Automation)
Purpose | Operators import contacts, compose campaigns, confirm send, and walk away. The browser never sends bulk mail.
Core rule | Send creates an immutable CampaignSend snapshot. Background workers deliver at the provider rate. PostgreSQL is the source of truth.
Processes | Next.js app (UI + API) · BullMQ worker · PostgreSQL · Redis (job transport only)
Default UI theme | Dark teal operations console, with Bright / Dark toggle in the header
Local URL | http://localhost:3000
SCOPE BUILT
Area | Count | Status | Notes
Work packages listed | 30 | Completed | Foundation through UI polish, local auth bypass, and resilience
Operator screens | 13 | Completed | Dashboard, Contacts, Import, Segments, Suppression, Campaigns, wizard, detail, Templates, Settings, Audit logs
API routes | 34 | Completed | Auth, contacts, campaigns, templates, webhooks, health, metrics, unsubscribe
Database models | 18 | Completed | Users, contacts, campaigns, sends, recipients, events, suppression, imports, audit, settings, heartbeat
Background queues | 6 | Completed | Materialize, send, CSV import, webhooks, scheduled start, reconcile
Email providers | 5 | Completed | Amazon SES, SendGrid, Mailgun, Postmark, Fake (dev/load test)
Automated test files | 6 | Completed | Vitest: render, crypto, webhooks, provider, state machine, suppression
Bright / Dark theme | 1 | Completed | Header toggle; choice saved in the browser
PRODUCT BOUNDARY
Included |  |  | Not included (by design)

## Work Completed
Work completed in this project
Each row is a delivered capability.
# | Phase / area | What was built | What it does | Where it lives | Status | Notes
1 | Foundation | Next.js 16 App Router scaffold, TypeScript, Tailwind v4, shadcn/ui | Application shell, routing, UI kit, and project structure | src/app, src/components | Completed | Next.js 16 conventions followed from local docs
2 | Foundation | Prisma 6 schema + PostgreSQL + Docker Compose | Durable data store; Postgres and Redis start as containers | prisma/schema.prisma, docker-compose.yml | Completed | PostgreSQL is source of truth; Redis is job transport only
3 | Foundation | Architecture and operations documentation | System, ER, state machines, queues, webhooks, recovery, security | README.md, docs/ARCHITECTURE.md | Completed
4 | Auth (original) | Session cookies, login API, roles ADMIN / OPERATOR / VIEWER | Internal operators only; no public registration | src/lib/auth.ts, src/app/api/auth | Completed | Login later bypassed for local use
5 | Contacts | Contact list, search, pagination, tags, export CSV | Manage permission-based recipients | src/app/(app)/contacts, src/lib/contacts | Completed
6 | Contacts | Streamed CSV import with job progress | Import tens of thousands of rows without blocking the UI | src/app/api/contacts/import, src/worker/processors/import.ts | Completed | Invalid rows counted; job continues
7 | Contacts | Downloadable CSV import template | Operators can download a sample file next to Import CSV | public/templates/contacts-import-template.csv | Completed | Added on Contacts and Import screens
8 | Audience | Tags and segments with JSON filters | Target campaigns by tag, segment, all contacts, or manual list | src/app/(app)/segments, src/lib/campaigns/audience.ts | Completed
9 | Suppression | Suppression list (unsubscribe, bounce, complaint, manual) | Blocked addresses are never sent again | src/app/(app)/suppression, src/lib/email/suppression.ts | Completed
10 | Templates | HTML + text templates, versions, personalization, test send, duplicate | Safe merge fields with escaping and fallbacks | src/app/(app)/templates, src/lib/email/render.ts | Completed
11 | Campaigns | Campaign wizard (audience, content, schedule, confirm) | Operator confirms eligible count before send | src/app/(app)/campaigns/new | Completed | Large sends require an extra checkbox
12 | Campaigns | Immutable CampaignSend snapshot | HTTP request only snapshots; send never happens in the browser | src/lib/campaigns/send.ts | Completed | Idempotency key prevents double send
13 | Campaigns | Pause, resume, cancel + cancellation window | Control in-flight sends without resending completed recipients | src/app/api/campaigns/[id]/pause¦resume¦cancel | Completed | Cannot recall provider-accepted mail
14 | Workers | BullMQ workers: materialize, send, import, webhook, scheduled, reconcile | Background delivery at EMAIL_RATE_LIMIT_PER_SECOND | src/worker | Completed | jobId = campaignSendId:email
15 | Workers | Atomic claim of recipients before provider send | No duplicate delivery if workers crash or Redis reconnects | src/worker/processors/send.ts | Completed | Terminal statuses are never resent
16 | Providers | Adapter layer: SES, SendGrid, Mailgun, Postmark, Fake | Switch providers without changing campaign logic | src/lib/email/adapters, src/lib/email/provider.ts | Completed | Dev/load tests must use fake provider
17 | Webhooks | Signed webhook ingest per provider | Updates delivery status; unique providerEventId | src/app/api/webhooks/[provider], src/lib/email/webhooks.ts | Completed | Verify first, enqueue second
18 | Unsubscribe | Public unsubscribe page + signed token | One-click unsubscribe writes suppression and contact status | src/app/unsubscribe, src/lib/email/unsubscribe.ts | Completed | Token is tamper-resistant
19 | Dashboard | Intelligence dashboard: audience + delivery stats | Live campaign and delivery rates | src/app/(app)/dashboard, src/lib/dashboard.ts | Completed | Shows a clear alert if Postgres is down
20 | Ops | Health, ready, metrics APIs + worker heartbeat | Liveness, Postgres/Redis/worker readiness, queue depths | src/app/api/health, ready, metrics; src/worker/health.ts | Completed | Worker health on port 3001
21 | Ops | Audit logs UI and API | Who did what on campaigns, contacts, settings | src/app/(app)/audit-logs | Completed
22 | Ops | Settings: org, sending domain checklist, users | SPF/DKIM/DMARC checklist; operator users | src/app/(app)/settings | Completed | DNS is a console task, not an app trick
23 | Quality | Vitest suite (render, crypto, webhooks, provider, state machine, suppression) | Guards personalization, tokens, no-resend rules | tests | Completed | npm test
24 | Quality | Load-test script against fake provider | Measure enqueue and worker throughput without real recipients | scripts/load-test.ts | Completed | EMAIL_PROVIDER=fake only
25 | Deploy | Dockerfile, Compose, production README | App + worker + migrate services; standalone Next build | Dockerfile, docker-compose.yml, README.md | Completed
26 | UI polish | Rebrand to ICCPP Email Intelligence System | Teal operations console, grouped nav, live pulse, UTC clock | src/components/app-shell.tsx, globals.css | Completed | Default from-name ICCPP
27 | UI polish | Bright and Dark theme buttons on screen | Header segmented control; theme persists in the browser | src/components/theme-toggle.tsx, theme-provider.tsx | Completed | Default theme is Dark
28 | Local UX | Login gate removed for initial local use | /login redirects to dashboard; APIs use a local operator | src/proxy.ts, src/app/login/page.tsx, src/lib/auth.ts | Completed | Logout removed from shell
29 | Resilience | Graceful dashboard when database is down | Empty stats plus a Database is not running alert instead of a 500 page | src/lib/dashboard.ts, src/app/(app)/dashboard/page.tsx | Completed | Needs Docker Desktop for real data
30 | Resilience | Rate limiter fallback and Redis lazy connect | App stays up if Redis is not running yet | src/lib/rate-limit.ts, src/lib/queue/redis.ts | Completed

## Requirement updated
Requirement updated
payment gateway
donation home page

## Screens
Operator screens built
Screen | URL | What the operator can do | Nav group | Status
Intelligence dashboard | /dashboard | Audience health, delivery rates, campaign status; DB-down alert | Intelligence | Completed
Contacts | /contacts | Search, filter, paginate, export CSV, download import template, open import | Intelligence | Completed
CSV import | /contacts/import | Upload CSV, watch streamed import job progress, download template | Intelligence | Completed
Segments | /segments | Create and manage audience filters for campaigns | Intelligence | Completed
Suppression | /suppression | View and add suppressed emails (unsubscribe, bounce, complaint, manual) | Intelligence | Completed
Campaigns | /campaigns | List campaigns and statuses; open wizard or a campaign | Campaigns | Completed
New campaign | /campaigns/new | Wizard: audience, template, schedule, confirm eligible count, send | Campaigns | Completed
Campaign detail | /campaigns/[id] | Progress, pause, resume, cancel, preview, test send | Campaigns | Completed
Templates | /templates | List email templates | Campaigns | Completed
New template | /templates/new | Create HTML/text template with personalization | Campaigns | Completed
Template detail | /templates/[id] | Edit, version, duplicate, send a test | Campaigns | Completed
Audit logs | /audit-logs | Inspect operator actions | Workspace | Completed
Settings | /settings | Org details, sending-domain checklist, users | Workspace | Completed
Unsubscribe (public) | /unsubscribe/[token] | Recipient opts out with a signed token | Public | Completed
Login (bypassed) | /login | Currently redirects to dashboard for local use | Public | Completed

## API Endpoints
API routes built
Method / area | Path | Purpose | Status
Auth | /api/auth/login | Create session (still present; UI login bypassed) | Completed
Auth | /api/auth/logout | Destroy session | Completed
Auth | /api/auth/me | Current operator | Completed
Contacts | /api/contacts | List / create contacts | Completed
Contacts | /api/contacts/[id] | Get / update / archive a contact | Completed
Contacts | /api/contacts/import | Start CSV import job | Completed
Contacts | /api/contacts/import/[id] | Import job progress | Completed
Contacts | /api/contacts/export | Export CSV | Completed
Tags | /api/tags | List / create tags | Completed
Segments | /api/segments | List / create segments | Completed
Suppression | /api/suppression | List / add suppressions | Completed
Templates | /api/templates | List / create templates | Completed
Templates | /api/templates/[id] | Get / update template | Completed
Templates | /api/templates/[id]/duplicate | Duplicate template | Completed
Templates | /api/templates/[id]/test | Send a test email | Completed
Campaigns | /api/campaigns | List / create campaigns | Completed
Campaigns | /api/campaigns/[id] | Get / update campaign | Completed
Campaigns | /api/campaigns/audience | Preview eligible audience count | Completed
Campaigns | /api/campaigns/[id]/send | Confirm send — snapshot + enqueue only | Completed
Campaigns | /api/campaigns/[id]/pause | Pause in-flight send | Completed
Campaigns | /api/campaigns/[id]/resume | Resume paused send | Completed
Campaigns | /api/campaigns/[id]/cancel | Cancel remaining unsent recipients | Completed
Campaigns | /api/campaigns/[id]/progress | Live send progress | Completed
Campaigns | /api/campaigns/[id]/preview | Preview personalized message | Completed
Campaigns | /api/campaigns/[id]/test | Test send for a campaign | Completed
Webhooks | /api/webhooks/[provider] | SES / SendGrid / Mailgun / Postmark / fake events | Completed
Public | /api/unsubscribe/[token] | Process unsubscribe token | Completed
Dashboard | /api/dashboard | Aggregated intelligence stats | Completed
Ops | /api/health | Liveness | Completed
Ops | /api/ready | Postgres, Redis, worker heartbeat | Completed
Ops | /api/metrics | Queue depths and failed deliveries | Completed
Ops | /api/audit-logs | Audit trail | Completed
Ops | /api/settings | Org and sending settings | Completed
Ops | /api/users | Operator users | Completed

## Data and Queues
Database models and background queues
DATABASE MODELS
Model | Role in the system | Key rules | Status
User / Session / LoginAttempt | Internal operators and sessions | Roles ADMIN, OPERATOR, VIEWER; no public signup | Completed
Contact / Tag / ContactTag | Recipient directory | emailNormalized unique; status includes unsubscribed/bounced | Completed
Segment | Saved audience filter (JSON) | Used by campaigns | Completed
Template / TemplateVersion | Email content versions | Current version pointer; HTML + text + fallbacks | Completed
Campaign | Draft / scheduled / sending campaign | Audience type ALL, TAGS, SEGMENT, MANUAL | Completed
CampaignSend | Immutable snapshot at confirm-send | Unique campaignId and idempotencyKey | Completed
CampaignRecipient | One row per address in a send | Unique (send, email); unique idempotencyKey | Completed
EmailDelivery | Per-attempt provider result | Unique (recipient, attemptNumber) | Completed
EmailEvent | Provider webhook events | providerEventId unique — duplicates ignored | Completed
Suppression | Do-not-send list | emailNormalized unique | Completed
ImportJob | CSV import progress | Counts imported / duplicate / invalid / suppressed | Completed
AuditLog | Operator actions | Indexed by entity and user | Completed
Setting | Key/value org settings | JSON values | Completed
WorkerHeartbeat | Worker liveness | Used by /api/ready | Completed
BACKGROUND QUEUES (BullMQ)
Queue | Job | What it does | Status
campaign-materialize | Materialize audience | Resolve audience in EMAIL_BATCH_SIZE batches into CampaignRecipient rows | Completed
email-send | Deliver one email | One job per recipient; jobId = idempotencyKey; rate-limited | Completed
csv-import | Import contacts | Stream CSV from disk; continue on malformed rows | Completed
provider-webhook | Process events | Apply bounce/complaint/delivery after signature verify | Completed
campaign-scheduled | Delayed start | Start a campaign at scheduledAt | Completed
campaign-reconcile | Rebuild missing jobs | If Redis is lost, re-enqueue PENDING/QUEUED/stuck PROCESSING from Postgres | Completed
CAMPAIGN STATUSES
DRAFT to READY / SCHEDULED to QUEUING to QUEUED to SENDING to COMPLETED / PARTIALLY_FAILED / FAILED. Also PAUSED and CANCELLED.
DELIVERY STATUSES
PENDING to QUEUED to PROCESSING to SENT to DELIVERED (or BOUNCED / COMPLAINED / DEFERRED). Also SUPPRESSED, FAILED, CANCELLED, SKIPPED. SENT is never resent after pause/resume.

## Tech Stack
Technology used
Layer | Choice | Version / note | Why it is in the project
Web framework | Next.js App Router | 16.3.4 | UI + API in one app
Language | TypeScript | 5.x | Typed domain and API contracts
UI | React | 19.2.8 | Operator console
Styling | Tailwind CSS + shadcn/ui | Tailwind 4 | Teal operations theme, Bright/Dark
Theme | next-themes | 0.4.6 | Bright and Dark buttons persist locally
Database | PostgreSQL + Prisma | Postgres 16 / Prisma 6.16.3 | Source of truth for campaigns and recipients
Queue | Redis + BullMQ | Redis 7 / BullMQ 6 | Job transport; reconstructable from Postgres
Validation | Zod | 4.x | Request and env validation
Email | SES / SendGrid / Mailgun / Postmark / Fake | Adapters behind one provider interface | Swap providers without changing send path
CSV | csv-parse / csv-stringify | Streamed import and export | Large contact files
Auth crypto | bcryptjs + signed tokens | Passwords and unsubscribe tokens | Internal operators; tamper-resistant unsubscribe
Logging | pino | 10.x | Structured logs with campaign IDs
Tests | Vitest | 4.x | Critical path coverage
Containers | Docker Compose | app, worker, postgres, redis, migrate | Local and production-shaped deploy
Worker runtime | tsx | Separate process on port 3001 health | Must not run send from Next.js request

## How to run
Local run (what you need for real data)
Step | Command / action | Why
1 | Start Docker Desktop | Postgres and Redis run in containers. If the daemon is off, the dashboard shows Database is not running.
2 | Copy .env.example to .env (already done locally) | Environment: DATABASE_URL, REDIS_URL, EMAIL_PROVIDER=fake, secrets.
3 | docker compose up -d postgres redis | Start database and queue.
4 | npx prisma migrate deploy | Create tables.
5 | npx prisma db seed | Seed admin / sample data.
6 | npm run dev | Next.js UI + API at http://localhost:3000
7 | npm run worker (separate terminal) | Background send/import. Do not chain this after next dev in one command.
8 | Open http://localhost:3000/dashboard | Login is currently skipped; you land in the operator console.
9 | Use Bright / Dark in the header | Theme is saved in the browser.
10 | npm test | Run Vitest suite.
Note: npm run worker was previously chained after npm run dev in the same terminal, so the worker never started. Run the worker in its own terminal.